## 1. Overview
DPA Open Brain — Pipeline Evolution Project
Decision-Source Ingestion Pipeline v2.4 → Level 5 Optimizing ¦ Date: 2026-04-12
Attribute | Value
Project Name | DPA Pipeline Evolution (Level 3 → Level 5 Optimizing)
Pipeline Version | v2.4 (2026-04-08) — canonical template
Current Maturity | Level 3 — Operational (Phase 1 largely landed; telemetry / accuracy track partial)
Target Maturity | Level 5 — Optimizing
Report Date | 2026-04-12
Source of Truth | ontology/docs/decision-source-pipeline-template.md
Primary Owner | Data Engineer
Companion Owner | Platform Engineer
Runtime | dpa-retrieval (SQLite + vector embeddings + ontology-aware filtering)
Ontology | dpa-case.ttl (OWL) + SHACL shapes
Graph Backend | GraphDB (dpa-law)
Embedding Model | OpenAI text-embedding-3-small
MATURITY LEVEL SUMMARY
Level | Name | Description | Target Date | Status
Level 1 | Initial | Ad-hoc; no repeatable process | — | Passed
Level 2 | Repeatable | Documented steps; per-source scripts | — | Passed
Level 3 | Defined & Operational | 10-step ETVLV; 3 gates; R18 + case-identity gates | Current | CURRENT
Level 4 | Managed | Accuracy-based gates; gold-set F1 ≥ 0.90; telemetry | 2026-07-09 | Phase 2
Level 5 | Optimizing | Hybrid RAG; SHACL enforcement graph; auto-remediation | 2026-10-09 | Phase 3
PHASE SUMMARY
Phase | Name | Timeframe | Key Deliverable | Target Level
Phase 1 | Deduplication + Telemetry | 2–4 weeks | case_fingerprint gate (Steps 3/4/8) + companion telemetry wiring | Level 3+
Phase 2 | Accuracy Gates + Gold Set | 3 months | 60-decision gold set; Step 4 F1 ≥ 0.90; authority-case-number parsers | Level 4
Phase 3 | Hybrid RAG + Enforcement Graph | 6 months | Multi-retriever bank; SHACL enforcement layer; embedding drift gates | Level 5

## 2. Phase 1 - Deduplication
Phase 1 — Composite case_fingerprint Deduplication Gate
Timeframe: 2–4 weeks ¦ Owner: Data Engineer ¦ Target: Steps 3, 4, 8 ¦ Priority: BLOCKING
Task ID | Task Name | Pipeline Step | Description | Owner | Priority | Status | Success Criterion | Notes
P1-01 | Design case_fingerprint data model | Step 3 | Define 4-tier composite key: authority_case_number → content_sha256 → filename_hash → synthetic escape. Add fingerprint_tier field to schema. | Data Eng | CRITICAL | Done | Schema PR merged to dpa-case.ttl; field documented in canonical template | Implemented in dpa-case.ttl and template v2.4
P1-02 | Implement fingerprint generation function | Step 3 | Python function compute_case_fingerprint(doc) with null-handling for each tier. Assign at Segment+Classify before chunk creation. | Data Eng | CRITICAL | Done | Unit tests pass for all 4 tiers; zero null fingerprints after Step 3 | compute_case_fingerprint() ships with unit tests; 4-tier ladder implemented
P1-03 | Add Criterion 6 to Step 4 gate | Step 4 | SQL assertion: SELECT case_fingerprint, COUNT(*) FROM batch_staging GROUP BY case_fingerprint HAVING COUNT(*) > 1. Gate fails if any row returned. | Data Eng | CRITICAL | Done | Step 4 gate rejects batch with duplicate fingerprints; failure logged with colliding doc IDs | gate_case_identity.py enforces Criterion 6 with sub-assertions
P1-04 | Add R19 rule to Step 8 gate | Step 8 | New R19: SELECT COUNT(DISTINCT case_fingerprint) == expected_case_count FROM corpus WHERE source = new_corpus. Failure routes to Step 3 re-segmentation. | Data Eng | CRITICAL | Done | R19 assertion passes for all new batches; R18 dryrun updated to assert R19 JSON exists | R19 gate implemented; R18 now checks R19 / fingerprint artifacts
P1-05 | Implement cross-batch collision gate | Step 4 / Step 5 | Pre-load check: compare new batch fingerprints against live corpus. SELECT fp FROM live_corpus WHERE fp IN (batch_fingerprints). Block if collision found. | Data Eng | HIGH | Partial | Zero cross-batch collisions pass through to Step 6; collision report saved to ontology/reports/ | Implemented; PASS artifacts located for EDPS/PDPC/DPC/ICO; ODPC report coverage not evidenced here
P1-06 | Remediate PDPC 207 duplicate cases | Post-Step 8 | Audit existing PDPC corpus. Identify 207 duplicates via content_sha256. Dry-run dedup. Apply canonical merge (keep highest-tier fingerprint record). Re-verify. | Data Eng | HIGH | Done | PDPC corpus distinct-case count matches expected manifest; R19 passes for PDPC | Applied 2026-04-10: 213 docs deleted, 2196 chunks reassigned
P1-07 | Build authority-case-number parser: PDPC | Step 2 | Regex extractor for PDPC case reference format from PDF body text. Output: authority_case_number field in canonical schema record. | Data Eng | HIGH | Done | Parser extracts case number for ≥ 90% of PDPC PDFs in test set | Parser shipping in authority_case_parsers.py
P1-08 | Build authority-case-number parser: DPC | Step 2 | Regex/LLM extractor for DPC Ireland case reference format. | Data Eng | HIGH | Done | Parser extracts case number for ≥ 90% of DPC PDFs in test set | Parser shipping in authority_case_parsers.py
P1-09 | Build authority-case-number parser: ICO | Step 2 | Regex/LLM extractor for ICO UK case reference format. | Data Eng | MEDIUM | Done | Parser extracts case number for ≥ 90% of ICO PDFs in test set | Parser shipping in authority_case_parsers.py
P1-10 | Add pre-ingest PDF hash check | Step 2 | Content-hash check at start of Step 2: has this PDF already been ingested? Block re-ingestion. Log as duplicate-prevented. | Data Eng | HIGH | Done | Zero re-ingestion of already-loaded PDFs; fast-fail at Step 2 before extraction | pre_ingest_pdf_hash_check.py ships with audit/dry-run/strict modes
P1-11 | Update canonical template (v2.4) | Governance | Write case_fingerprint spec, Criterion 6, R19, and pre-ingest hash check into decision-source-pipeline-template.md as v2.4. | Data Eng | CRITICAL | Done | Template v2.4 merged; SKILL.md and ops-pack updated to reference v2.4 | Template settled at v2.4 on 2026-04-08
P1-12 | Update R18 dryrun script | Step 8 / R18 | Add assertions for: (a) R19 gate JSON exists, (b) cross-batch collision report exists, (c) fingerprint_tier distribution in VERIFY workbook. | Data Eng | HIGH | Done | R18 exits 0 for a clean Phase 1 batch; fails with named assertion for any missing artifact | Implemented; check-completion-report.py now carries A1–A9, not only A1–A6
P1-13 | Canary run with Phase 1 gates | All steps | Run one source (recommend EDPS — smallest corpus) through full Phase 1 pipeline. Verify all new gates fire correctly. | Data Eng | HIGH | Partial | Canary batch passes all gates; workbooks contain fingerprint_tier column; R18 exits 0 | EDPS Phase 1 canary PASS; PDPC canary artifact failed on bad DB path, though PDPC Step 4/R19 artifacts exist
P1-14 | Wire companion-process telemetry | Companion | Verify pass/fail telemetry is wired for all 3 companion processes (Triple Store Sync, Incremental Reasoning, Runtime Bridge). Add batch heartbeat logging. | Platform Eng | HIGH | Partial | All 3 companion processes emit pass/fail per batch; failures surface in monitoring dashboard | Heartbeat module + tests exist; no heartbeat files on disk and emitter wiring not evidenced

## 3. Phase 2 - Accuracy Gates
Phase 2 — Gold-Standard Test Set & Accuracy-Based Gate Upgrade
Timeframe: 3 months ¦ Owner: Data Engineer + Research ¦ Target: Step 4 F1 ≥ 0.90 ¦ Target Level: 4
Task ID | Task Name | Pipeline Step | Description | Owner | Priority | Status | Success Criterion | Dependency
P2-01 | Scope and recruit dual annotators | Research | Identify two domain-expert annotators for 60-decision gold set. Define annotation guidelines aligned with E1–E6 error classes. Set up annotation environment. | Research | HIGH | Open | Two annotators confirmed; guidelines document published; annotation tool configured | None
P2-02 | Select 60-decision gold set | Research | Stratified sample: 15 PDPC + 15 DPC + 15 ICO + 15 EDPS decisions. Stratify by document_type, decision_date range, and sanction complexity. | Research | HIGH | Not started | 60 PDFs selected; selection rationale documented; PDFs archived at ontology/gold-set/ | P2-01
P2-03 | Dual-annotate gold set | Research | Both annotators independently label all 60 decisions using E1–E6 error taxonomy. Produce annotation files per document. | Research | HIGH | Not started | All 60 decisions annotated by both annotators; annotation files saved | P2-02
P2-04 | Compute inter-annotator agreement | Research | Calculate Cohen's κ across all annotation pairs. κ ≥ 0.80 required. If κ < 0.80, adjudicate disagreements and re-annotate disputed items. | Research | HIGH | Not started | Cohen's κ ≥ 0.80 confirmed; adjudication log saved; final gold set frozen | P2-03
P2-05 | Freeze gold set as Research Protocol P2-07 | Research | Publish frozen gold set as canonical ground truth under Research Protocol P2-07. Version-control the set. No further modifications without protocol revision. | Research | HIGH | Not started | P2-07 protocol document published; gold set files SHA-256 hashed and recorded | P2-04
P2-06 | Build F1 evaluation harness | Step 4 | Python script: run extraction pipeline against gold set, compare outputs to gold labels, compute F1 per error class (E1–E6) and overall. Output: evaluation_report.json. | Data Eng | HIGH | Not started | Harness produces evaluation_report.json with per-class F1 and overall F1; reproducible | P2-05
P2-07 | Baseline extraction F1 measurement | Step 4 | Run current extraction pipeline against gold set. Establish baseline F1 scores per error class. Document gaps to F1 ≥ 0.90 target. | Data Eng | HIGH | Not started | Baseline F1 report published; gap to 0.90 target quantified per error class | P2-06
P2-08 | Iterate extraction to reach F1 ≥ 0.90 | Steps 2–3 | Targeted extraction improvements per error class (E1: missing field parsers, E2: value normalisation, E3: format standardisation, E4: relation extraction, E5: date parsing, E6: ontology mapping). | Data Eng | HIGH | Not started | Overall extraction F1 ≥ 0.90 on gold set; per-class F1 documented | P2-07
P2-09 | Upgrade Step 4 gate to accuracy-based | Step 4 | Replace completeness-only Criterion 1 (≥95% completeness) with accuracy gate: F1 ≥ 0.90 on sampled documents against gold set. Keep criteria 2–5 unchanged. | Data Eng | CRITICAL | Open | Step 4 gate rejects batches with F1 < 0.90; gate is named replaceable component | P2-08
P2-10 | Build authority-case-number parser: EDPS | Step 2 | Regex/LLM extractor for EDPS case reference format. Complete the parser set across all 4 current sources. | Data Eng | MEDIUM | Not started | Parser extracts case number for ≥ 90% of EDPS PDFs in test set | P1-07 through P1-09 complete
P2-11 | Schema drift remediation | Step 2 | Audit metadata field consistency across all 4 sources. Produce canonical metadata mapping for jurisdiction-specific field variations. Update per-source adapters. | Data Eng | MEDIUM | Partial | All sources produce identical canonical schema fields; no null jurisdiction_iri rows | None
P2-12 | Update canonical template (v2.5) | Governance | Write gold-set protocol reference, F1 gate specification, and per-source parser requirements into template v2.5. | Data Eng | HIGH | Open | Template v2.5 merged; R18 updated to assert evaluation_report.json exists for accuracy-gated batches | P2-09

## 4. Phase 3 - Level 5
Phase 3 — Hybrid RAG Architecture + SHACL Enforcement Graph
Timeframe: 6 months ¦ Owner: Data Eng + Platform Eng ¦ Target: Level 5 Optimizing
Task ID | Task Name | Component | Description | Owner | Priority | Status | Success Criterion | Literature Basis
P3-01 | Add BM25 sparse retriever | Retrieval Layer | Implement BM25 full-text index alongside existing vector index. Expose via retrieval_search_by_bm25 MCP tool. Integrate into Step 7 atomic indexing. | Platform Eng | HIGH | Not started | BM25 index populated for all corpora; MRR improvement ≥ 5% on benchmark query set | HybridRAG (arXiv:2408.04948)
P3-02 | Add KG graph traversal retriever | Retrieval Layer | Implement SPARQL-based graph traversal retriever over GraphDB dpa-law. Expose via retrieval_search_by_graph MCP tool. One-hop entity expansion for regulatory citations. | Platform Eng | HIGH | Scaffold only | Graph retriever returns relevant triples for ≥ 80% of legal-analysis benchmark queries | HetaRAG (arXiv:2509.21336)
P3-03 | Build dynamic query router | Retrieval Layer | Query analysis component: classify query type (factual, relational, semantic) and route to appropriate retriever(s) or multi-retriever fusion. | Platform Eng | HIGH | Not started | Router correctly classifies ≥ 90% of benchmark queries; latency < 200ms overhead | RAG+KAG (DOI:10.1109/iaeac65194)
P3-04 | Implement reciprocal rank fusion reranker | Retrieval Layer | Fuse candidates from all retrievers using Reciprocal Rank Fusion (RRF). No training required. Implement as post-retrieval step before generation. | Platform Eng | MEDIUM | Not started | RRF reranker improves nDCG@10 ≥ 8% vs single-retriever baseline on held-out query set | Training-Free Hybrid (DOI:10.5753/sbbd.2025)
P3-05 | Embedding drift detection gate | Step 7 | Add embedding quality gate to Step 7: compute cosine similarity distribution for new corpus embeddings; flag if mean similarity < threshold or distribution shifts > 2σ from baseline. | Data Eng | HIGH | Not started | Embedding gate fires correctly on synthetic drift test; no silent low-quality embeddings reach index | Semantic chunking & embedding quality (NAACL 2024)
P3-06 | Recall@k monitoring gate | Step 8 | Add Recall@k (k=5,10) metric to Step 8 corpus verification query pack. Baseline from Phase 2 gold set. Gate fails if Recall@k drops > 10% vs baseline. | Data Eng | HIGH | Not started | Recall@5 and Recall@10 computed and logged for every batch; regression triggers Step 10 | RAG vs GraphRAG (arXiv:2502.11371)
P3-07 | Evolve dpa-case.ttl: add SHACL enforcement shapes | Ontology | Add normative SHACL shapes to dpa-case.ttl: (a) sh:MinCountConstraintComponent for required fields, (b) sh:ClassConstraintComponent for owl_class_iri specificity, (c) sh:PatternConstraintComponent for case_fingerprint format, (d) sh:SPARQLConstraintComponent for cross-entity consistency. | Data Eng | CRITICAL | Partial (shadow) | All SHACL shapes validate correctly against test instances; shapes committed to dpa-case.ttl | GUCON framework; SHACL-ACL; GDPR SHACL (Pandit 2018)
P3-08 | Integrate SHACL validation into Step 4 gate | Step 4 | Replace manual criterion checks 2–5 with SHACL validation report. Gate passes only if sh:conforms = true. Failure report saved as gate JSON. | Data Eng | CRITICAL | Partial (shadow) | Step 4 gate produces SHACL validation report JSON; R18 asserts its existence; non-conformant batches blocked | SHACL as enforcement layer (literature)
P3-09 | Separate OWL descriptive from SHACL normative | Ontology | Refactor dpa-case.ttl: OWL handles entity classification and inference; SHACL shapes handle closed-world constraint enforcement. Two named graphs: :descriptive and :normative. | Data Eng | HIGH | Done | Two named graphs present in dpa-case.ttl; OWL reasoner and SHACL validator operate independently | Descriptive vs normative separation (ISWC 2023)
P3-10 | Add deontic policy rules to enforcement graph | Ontology | Model permissions, obligations, and prohibitions as SHACL-SPARQL constraints: e.g., OBLIGATION: every SupervisoryDecision must have a holding chunk; PROHIBITION: synthetic fixtures must not enter production corpus. | Data Eng | HIGH | Done | Deontic rules expressed as SHACL-SPARQL shapes; all rules pass on clean test corpus; synthetic fixture prohibition tested | GUCON; Compliance checking via W3C (2024)
P3-11 | Add provenance nodes to enforcement graph | Ontology | Add PROV-O style provenance nodes to each ingested decision: prov:wasGeneratedBy (extraction script version), prov:wasDerivedFrom (source PDF hash), prov:generatedAtTime (ingestion timestamp). | Data Eng | MEDIUM | Partial | Every decision node has 3 provenance triples; SPARQL provenance query returns full lineage for any decision | PROV-O; GDPR provenance (Pandit 2018)
P3-12 | Implement automated remediation loop | Step 10 | Extend Step 10 with self-correction agent: SHACL validation report → classify error type → select remediation action → dry-run → apply → re-validate. Fully automated for E1/E3/E6 error classes. | Data Eng | MEDIUM | Partial | Automated remediation resolves ≥ 60% of E1/E3/E6 errors without human intervention | Agentic AI enforcement (arXiv G-SPEC 2512.20275)
P3-13 | Implement cross-backbone ranking balance monitor | Step 9 | Add ranking balance metric to Step 9: measure corpus representation in top-k results across all sources. Flag if new corpus < 5% of top-20 results for relevant query types. | Data Eng | MEDIUM | Not started | Ranking balance metric computed for every Step 9 run; imbalance triggers reranker weight adjustment | RAG vs GraphRAG systematic evaluation (2025)
P3-14 | Update canonical template (v3.0) | Governance | Write hybrid RAG architecture, enforcement graph specification, SHACL gate integration, and automated remediation into template v3.0. This constitutes the Level 5 canonical definition. | Data Eng | CRITICAL | Not started | Template v3.0 merged; marks official Level 5 architecture; all downstream docs updated | Single source of truth governance rule

## 5. Step Evolution Table
Per-Step Pipeline Evolution: Current → Phase 1 → Phase 2 → Phase 3 (Level 5)
What changes at each of the 10 pipeline steps across the three evolution phases
Step | Stage | Step Name | Current (v2.3 — Level 3) | Phase 1 Addition (Dedup) | Phase 2 Addition (Accuracy) | Phase 3 Addition (Level 5) | Gate Type at Level 5
1 | EXTRACT | Source Acquisition | Raw acquisition; fetch failures logged; no hash check | No change | No change | Streaming ingestion trigger; auto-classification of source type | Completion
2 | EXTRACT | Extract + Transform | Canonical schema extraction; 4 fast-fail sanity checks; no pre-ingest hash check | Pre-ingest PDF content-hash check (fast-fail if already ingested); authority-case-number parsers per source | E1–E6 error classification on extracted fields; extraction logged against gold-set schema | LLM-assisted extraction with confidence scoring; structured output validation | Completion + fast-fail hash gate
3 | TRANSFORM | Segment + Classify | Chunk type assignment from canonical family; owl_class_iri and shacl_shape_iri assigned | case_fingerprint computed (4-tier precedence); fingerprint_tier field assigned | Extraction confidence score per chunk; chunk-level error class tagging | KG-linked chunking: entity seeds extracted for graph traversal; chunks linked to ontology nodes | Completion
4 | VALIDATE | Pre-Load Validate ◆ GATE | 5 criteria: completeness ≥95%, no dup IDs, chunk types, specific owl_class_iri, IRI resolution | + Criterion 6: case_fingerprint uniqueness within batch; cross-batch collision check vs live corpus | Criterion 1 upgraded: F1 ≥ 0.90 against gold set (replaces completeness-only check) | Full SHACL validation report replaces manual criteria 2–5; sh:conforms = true required | ◆ QUALITY GATE (SHACL-enforced at Level 5)
5 | VALIDATE | Batch Preparation | Idempotent batch files; manifest with checksums, schema version, extraction script version | Manifest includes fingerprint_tier distribution and cross-batch collision report reference | Manifest includes F1 score and evaluation_report.json reference | Manifest includes SHACL validation report reference and provenance node hashes | Completion
6 | LOAD | Retrieval Load | Idempotent document + chunk registration; retry with exponential backoff; SQLite busy-timeout | No change (dedup gate at Step 4 prevents duplicates reaching Step 6) | No change | No change (gate enforcement upstream means load is clean) | Completion ← CRITICAL PATH ENDS
7 | LOAD | Embed and Index (atomic) | Embedding generation + ontology_index sync in single atomic step; 2-part completion check | No change | No change | + BM25 sparse index population (atomic with embedding); + KG node linking for graph retriever; + embedding drift detection gate | Completion + embedding quality gate
8 | VERIFY | Corpus Verification ◆ GATE | Ontology-index parity assertion first; source-specific query pack via real MCP tools | + R19 rule: distinct-case count == expected manifest count | + Recall@k baseline assertion (k=5, k=10) vs gold-set benchmark | + Recall@k regression gate (< 10% drop allowed); + SHACL post-load conformance spot-check | ◆ QUALITY GATE
9 | VERIFY | Cross-Backbone Verification ◆ GATE | Baseline + diversified mode validators; both outputs persisted; ranking imbalance detection | No change | No change | + Ranking balance monitor: new corpus ≥ 5% of top-20 results; + graph retriever cross-backbone check | ◆ QUALITY GATE
10 | VERIFY | Remediation | Routing: extraction→Steps 2–4; segmentation→Steps 3–4; load→Steps 6–7; verify→audit/dry-run/apply | No change (fingerprint errors route to Step 3 re-segmentation) | F1 regression errors route to extraction improvement loop (Steps 2–3) | Automated remediation agent for E1/E3/E6 error classes; SHACL report drives action selection | Feedback loop (automated at Level 5)

## 6. Risk Register
Open Gaps Risk Register — 10 Identified Gaps from Pipeline §10
Risk levels: HIGH = blocks retrieval quality / audit integrity ¦ MEDIUM = degrades accuracy ¦ LOW = operational debt
Gap ID | Gap Description | Risk Level | Risk Rationale | Current State | Proposed Mitigation | Phase | Owner | Status
G01 | No ontology-level case identity rule — IRI local name is throwaway sequence; two rows for same PDF are indistinguishable | HIGH | 21.7% duplication observed in PDPC (207 of 952 rows). Every new source onboarded multiplies this risk. | case_fingerprint ontology + gates ship; rollout evidence strongest for EDPS/PDPC/DPC/ICO | Composite case_fingerprint (P1-01/P1-02); Criterion 6 at Step 4; R19 at Step 8 | Phase 1 | Data Eng | PARTIALLY CLOSED — implemented in repo
G02 | Inter-run cross-source collision not addressed — Step 4 checks within-batch only; two batches can load same decision under different source_prefix | HIGH | Silent duplication across sources; retrieval returns duplicate results; audit count inflated. | Cross-corpus collision gate implemented; report coverage not yet evidenced for every source | Cross-batch collision gate at Step 4/5 comparing new batch fingerprints against live corpus (P1-05) | Phase 1 | Data Eng | PARTIALLY CLOSED — gate implemented
G03 | Step 4 gate is completeness-based, not accuracy-based — F1 ≥ 0.90 path named but not built | MEDIUM | Extraction errors (wrong field values, missing relations) pass the gate undetected. Retrieval returns structurally valid but semantically incorrect chunks. | Completeness ≥ 95% only; no accuracy measurement | Gold set construction (P2-01 to P2-05); F1 harness (P2-06); gate upgrade (P2-09) | Phase 2 | Data Eng + Research | OPEN — P2
G04 | Authority-case-number parsers do not exist for any source — case numbers in PDF body text only | MEDIUM | Fingerprint falls through to content_sha256 tier for all current sources; authority_case_number (apex tier) unused. | PDPC/DPC/ICO parsers ship; EDPS parser not yet built | Per-source parsers: PDPC (P1-07), DPC (P1-08), ICO (P1-09), EDPS (P2-10) | Phase 1–2 | Data Eng | PARTIALLY CLOSED — 3 of 4 parsers ship
G05 | Companion-process telemetry named as requirement but wiring not independently verified for all 3 processes | MEDIUM | Non-blocking silently becomes silently broken (Lesson 10). Triple Store Sync or Runtime Bridge could fail for multiple batches without detection. | Heartbeat module/tests exist; no emitted heartbeat files on disk | Verify and wire pass/fail telemetry for all 3 companion processes; batch heartbeat logging (P1-14) | Phase 1 | Platform Eng | PARTIAL — scaffolding only
G06 | Gold-standard test set scoped (P2-07/P2-09) but not built — 60 decisions, dual-annotator, κ ≥ 0.80 | MEDIUM | Step 4 cannot measure extraction accuracy until gold set exists. F1 gate upgrade blocked. | Research Protocol P2-07 scoped; annotators not recruited | Dual-annotator sprint (P2-01 to P2-05); freeze gold set as P2-07 protocol | Phase 2 | Research | OPEN — P2
G07 | R18 dryrun enforced going forward but retroactive gaps remain — PDPC and DPC pre-R18 batches lack all 5 stage workbooks | LOW | Retroactive audit reconstruction for pre-R18 batches requires manual effort. Not a forward-looking risk. | PDPC/DPC batches pre-dating R18 missing workbooks | One-time retroactive workbook sweep (classified as remediation, not operational pattern) | Phase 1 (one-time) | Data Eng | OPEN — low urgency
G08 | No formal pre-ingest hash check at Step 2 — re-ingestion of already-loaded PDFs not blocked at source | HIGH | Allows Defect Class 8 (cross-loader duplication) to enter pipeline before any gate can catch it. | pre_ingest_pdf_hash_check.py implemented with tests | Pre-ingest PDF content-hash fast-fail at Step 2 (P1-10) | Phase 1 | Data Eng | CLOSED — implemented
G09 | Schema drift across jurisdictions — metadata field inconsistencies between sources | LOW | Canonical schema records have inconsistent field coverage across sources. Retrieval filtering by jurisdiction_iri or authority_tier may return incomplete results. | Some remediation tooling/logging exists; no systematic drift program | Canonical metadata mapping audit; per-source adapter standardisation (P2-11) | Phase 2 | Data Eng | PARTIAL — remediation pieces exist
G10 | SHACL validation performance under large-batch load — resource contention during validation | MEDIUM | SHACL validation at Step 4 for large batches (> 500 documents) may cause timeout or memory pressure in SQLite + MCP server environment. | SHACL not yet integrated; performance unknown | Targeted reasoning + entity merging before validation (P3-07/P3-08); parallel validation design | Phase 3 | Platform Eng | OPEN — P3

## 7. Defect Class Tracker
Defect Class Tracker — 11 Empirical Defect Classes (§9 Pipeline Document)
Sources: PDPC (2026-03), DPC Ireland (2026-03), ICO UK (2026-04), EDPS (2026-04)
Class ID | Defect Name | First Observed | Current Defence | Confidence | Defence Adequacy vs Best Practice | Phase 1 Enhancement | Status
D01 | Three-definition drift | PDPC (2026-03) | Single canonical template; governance rule; CLAUDE.md read-first protocol | High | ADEQUATE — Single-source-of-truth governance matches best-practice 'metadata control plane' pattern. Template versioning (v2.1→v2.3) demonstrates active maintenance. | No change required | DEFENDED
D02 | Missing embedding step | PDPC (2026-03) | Step 7 atomic; ontology_index sync in same script | High | ADEQUATE — Atomic step design eliminates the operator-error failure mode. Two-part completion check provides mechanical verification. | Phase 3: extend atomicity to include BM25 and KG indexing | DEFENDED
D03 | Generic owl_class_iri payloads | DPC Ireland (2026-03) | Step 4 gate criterion 4 (chunk-type-specific IRI required) | High | ADEQUATE — Gate criterion directly blocks the defect. Aligns with SHACL sh:ClassConstraintComponent best practice. | Phase 3: replace manual criterion with SHACL shape | DEFENDED
D04 | Ontology-index empty after load | ICO UK (2026-04) | Step 7 two-part completion check + Step 8 parity assertion evaluated first | High | ADEQUATE — Two independent checks (completion + gate) provide defence-in-depth. Parity assertion is evaluated before query pack, preventing false passes. | No change required | DEFENDED
D05 | Narrative drift in completion reports | ICO UK (2026-04) | R18 dryrun check; three-tier report structure | High for new batches | ADEQUATE for new batches — R18 mechanically enforces evidence-before-narrative. Three-tier structure separates facts from interpretation. Retroactive gap remains. | Phase 1: R18 updated to assert R19 JSON and fingerprint report | DEFENDED (new batches)
D06 | Workbooks written to /tmp, then lost | ICO UK (2026-04) | /tmp banned; canonical path ontology/reports/; R18 asserts existence | High | ADEQUATE — Canonical path + mechanical assertion + ban on /tmp matches immutable-storage best practice for audit artifacts. | No change required | DEFENDED
D07 | Multi-mode validator results lost | ICO UK (2026-04) | Multi-mode persistence rule; R18 asserts all modes on disk | High | ADEQUATE — Explicit persistence rule + R18 assertion provides mechanical enforcement. Matches 'automate capture of all artifacts at runtime' best practice. | No change required | DEFENDED
D08 | Cross-loader case duplication | PDPC (discovered 2026-04-08) | NO CURRENT DEFENCE — 207 duplicates in 952 rows (21.7%) | GAP — OPEN | INADEQUATE — No identity predicate, no dedup gate, no cross-batch check. Best practice requires blocking+fingerprinting+history-aware merge detection. This is the highest-priority open defect. | Phase 1: case_fingerprint (P1-01/P1-02), Criterion 6 (P1-03), R19 (P1-04), cross-batch gate (P1-05) | GAP — OPEN
D09 | Synthetic fixture leakage into production | R-PDPC-01 (2026-04-05) | Dev-seed detection + quarantine | Medium | PARTIALLY ADEQUATE — Detection and quarantine exist but 23 hashless legacy rows and 35 policy B1 stubs remain under investigation. Best practice requires mandatory hash for all records. | Phase 1: pre-ingest hash check (P1-10) prevents future hashless records | PARTIAL — MONITORING
D10 | Companion-process silent failure | Lesson 10 (pre-emptive) | Pass/fail telemetry per batch required (not yet wired) | Medium | INADEQUATE — Telemetry is specified but not verified as wired for all 3 processes. Best practice: automated pass/fail logging with alerting. Non-blocking ≠ invisible. | Phase 1: wire and verify telemetry for all 3 companion processes (P1-14) | GAP — OPEN
D11 | Legacy corpora distorting evaluation | Lesson 7 | Harmonisation via legacy-regulatory-normalization script | Medium | PARTIALLY ADEQUATE — Normalisation script exists but medium confidence. Cross-backbone ranking balance monitor (Phase 3) will provide ongoing detection. | Phase 3: ranking balance monitor in Step 9 (P3-13) | PARTIAL — MONITORING

## 8. Success Metrics & KPIs
Success Metrics & KPIs — Pipeline Evolution to Level 5
Metrics define 'done' for each phase and the operational baseline at Level 5 Optimizing
Metric ID | Metric Name | Category | Current Baseline | Phase 1 Target | Phase 2 Target | Phase 3 / Level 5 Target | Measurement Method | Gate / Rule
M01 | Corpus Deduplication Rate | Deduplication | 78.3% (21.7% duplicate rate in PDPC) | ≥ 99% (< 1% duplicates) | ≥ 99.5% | 100% | SELECT COUNT(DISTINCT case_fingerprint) / COUNT(*) FROM corpus | R19 (Step 8)
M02 | Cross-Batch Collision Rate | Deduplication | Unknown (no gate) | 0 collisions per batch | 0 collisions per batch | 0 collisions per batch | Cross-batch collision gate report at Step 4/5 | Criterion 6 + cross-batch gate
M03 | Fingerprint Tier Distribution (Apex %) | Deduplication | 0% (no parsers) | ≥ 30% authority_case_number tier | ≥ 60% authority_case_number tier | ≥ 80% authority_case_number tier | fingerprint_tier column distribution in VALIDATE workbook | Step 3 completion check
M04 | Extraction F1 Score (Overall) | Accuracy | Unmeasured (no gold set) | N/A (gold set not built) | ≥ 0.90 overall F1 | ≥ 0.95 overall F1 | evaluation_report.json vs frozen gold set P2-07 | Step 4 gate (Phase 2+)
M05 | Extraction F1 — E1 Missing Field | Accuracy | Unmeasured | N/A | ≥ 0.90 | ≥ 0.95 | Per-class F1 in evaluation_report.json | Step 4 gate
M06 | Extraction F1 — E6 Ontology Mapping | Accuracy | Unmeasured | N/A | ≥ 0.88 | ≥ 0.93 | Per-class F1 in evaluation_report.json | Step 4 gate
M07 | Inter-Annotator Agreement (Cohen's κ) | Accuracy | N/A (no gold set) | N/A | ≥ 0.80 (gate to freeze gold set) | ≥ 0.80 (maintained on gold set updates) | κ computed during P2-04 annotation | P2-04 freeze criterion
M08 | Recall@5 (Corpus Verification) | Retrieval | Not measured | Baseline established | Baseline ± 5% | Baseline + ≥ 10% improvement | Step 8 query pack Recall@5 measurement | Step 8 gate (Phase 2+)
M09 | Recall@10 (Corpus Verification) | Retrieval | Not measured | Baseline established | Baseline ± 5% | Baseline + ≥ 10% improvement | Step 8 query pack Recall@10 measurement | Step 8 gate (Phase 2+)
M10 | nDCG@10 (Cross-Backbone) | Retrieval | Not measured | Baseline established | Baseline ± 5% | Baseline + ≥ 8% vs single-retriever | Step 9 cross-backbone validator nDCG@10 | Step 9 gate
M11 | Ranking Balance — New Corpus Share | Retrieval | Not measured | Baseline established | ≥ 5% of top-20 results | ≥ 8% of top-20 results | Step 9 ranking balance monitor (P3-13) | Step 9 gate (Phase 3)
M12 | Embedding Coverage | Embedding | 100% (enforced by Step 7) | 100% | 100% | 100% | count(embeddings) == count(chunks) for corpus | Step 7 completion check
M13 | Embedding Drift Score | Embedding | Not measured | Baseline established | < 2σ drift from baseline | < 1.5σ drift from baseline | Cosine similarity distribution check in Step 7 gate (P3-05) | Step 7 gate (Phase 3)
M14 | R18 Dryrun Pass Rate | Audit | 100% for post-R18 batches | 100% | 100% | 100% | check-completion-report.py exit code | R18 (all batches)
M15 | Stage Workbook Completeness | Audit | 100% for post-R18 batches; retroactive gaps remain | 100% new batches | 100% all batches | 100% all batches | R18 assertion 1: all 5 workbooks exist at canonical path | R18
M16 | Companion Process Telemetry Coverage | Governance | Unverified (0 of 3 confirmed) | 3 of 3 processes wired (P1-14) | 3 of 3 processes wired | 3 of 3 processes wired | Pass/fail log per batch per companion process | Companion telemetry rule
M17 | SHACL Conformance Rate | Ontology | Not applicable (SHACL not in gate) | N/A | N/A | 100% sh:conforms = true for loaded batches | SHACL validation report JSON at Step 4 (Phase 3) | Step 4 SHACL gate (Phase 3)
M18 | Automated Remediation Resolution Rate | Automation | 0% (all remediation manual) | 0% | 0% | ≥ 60% of E1/E3/E6 errors resolved without human intervention | Step 10 remediation agent log | Step 10 automated loop (Phase 3)